## getit css app
GetIT CSS App
Manage any type of project. Assign owners, set timelines and keep track of where your project stands.
Planning Sprint One
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
Initial Client Meeting |  |  |  | Done |  | 2023-08-04 | 2023-08-04
Elicit Client Requirements |  |  |  | Done |  | 2023-08-08 | 2023-08-11
User Stories |  |  |  | Done |  | 2023-08-07 | 2023-08-25
Gantt Chart Initial Draft |  | Alyssa Pilbrow |  | Working on it |  | 2023-08-07 | 2023-08-25
Budget Initial Draft |  |  |  | Working on it |  | 2023-08-07 | 2023-08-25
Risk Assessment Meeting |  |  |  | Done |  | 2023-08-18 | 2023-08-18
Risk Assessments Initial Draft |  |  |  | Working on it |  | 2023-08-14 | 2023-08-25
Planning Retrospective |  |  |  | Not Started |  | 2023-08-25 | 2023-08-25
Client Acceptance |  |  |  | Not Started |  | 2023-08-25 | 2023-08-25
[6 empty] | 2023-08-04 | 2023-08-25
Planning Sprint Two
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
UX/UI & Graphic Design: Requirements and Draft
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
Elicit Design Requirements |  |  |  | Not Started | High | 2023-09-04 | 2023-09-08
Draft Wireframes |  |  |  | Not Started | High | 2023-09-04 | 2023-09-08 | Elicit Client Requirements
Sprint Retrospective |  |  | 2023-09-08 | Not Started | Critical ⚠️️ | 2023-09-08 | 2023-09-08
Client Acceptance |  |  | 2023-09-08 | Not Started | Critical ⚠️️ | 2023-09-08 | 2023-09-08
|  |  | 2023-09-08 |  |  | 2023-09-04 | 2023-09-08
UX/UI & Graphic Design Sprint: Mockups
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
Wireframe Updated to Client Feedback |  |  |  | Not Started |  | 2023-09-11 | 2023-09-15 | Draft Wireframes
Mockups Version One |  |  |  | Not Started | High | 2023-09-18 | 2023-09-22 | Wireframe Updated to Client Feedback
Brand Guidelines Sheet Version One |  |  |  | Not Started | Medium | 2023-09-11 | 2023-09-22 | Elicit Design Requirements
Image Creation Version One |  |  |  | Not Started | Medium | 2023-09-11 | 2023-09-22 | Elicit Design Requirements
Logo Sheet |  |  |  | Not Started |  | 2023-09-11 | 2023-09-22 | Elicit Design Requirements
Sprint Retrospective |  |  | 2023-09-22 | Not Started | Critical ⚠️️ | 2023-09-22 | 2023-09-22
Client Acceptance |  |  | 2023-09-22 | Not Started | Critical ⚠️️ | 2023-09-22 | 2023-09-22
|  |  | 2023-09-22 |  |  | 2023-09-11 | 2023-09-22
UX/UI Design Sprint: Finalize Mockups
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
Final Mockups |  |  |  | Not Started |  | 2023-09-25 | 2023-09-29 | Mockups Version One
Finalize Brand Guidelines Sheet |  |  |  | Not Started |  | 2023-09-25 | 2023-09-29 | Brand Guidelines Sheet Version One
Finalize Logo |  |  |  | Not Started |  | 2023-09-25 | 2023-09-29 | Logo Sheet
Finalize Images |  |  |  | Not Started |  | 2023-09-25 | 2023-09-29 | Image Creation Version One
Sprint Retrospective |  |  | 2023-09-29 | Not Started |  | 2023-09-29 | 2023-09-29
Client Acceptance |  |  | 2023-09-29 | Not Started | Critical ⚠️️ | 2023-09-29 | 2023-09-29
|  |  | 2023-09-29 |  |  | 2023-09-25 | 2023-09-29
Public Holidays & Other Notable Dates
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
Canterbury Anniversary |  |  |  | Holiday |  | 2023-11-17 | 2023-11-17
Christmas Day |  |  |  | Holiday |  | 2023-12-25 | 2023-12-25
Boxing Day |  |  |  | Holiday |  | 2023-12-26 | 2023-12-26
New Year's Day |  |  |  | Holiday |  | 2024-01-01 | 2024-01-01
Day after New Year's Day |  |  |  | Holiday |  | 2024-01-02 | 2024-01-02
Waitangi Day |  |  |  | Holiday |  | 2024-02-06 | 2024-02-06
Buffer Period |  |  |  | Buffer Period | High | 2024-02-23 | 2024-02-29
[6 empty] | 2023-11-17 | 2024-02-29
Development Sprint: Backend
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
Define Backend Architecture |  |  |  | Not Started | High | 2023-09-25 | 2023-10-06
Set Up Development Enviroment |  |  |  | Not Started | Low | 2023-09-25 | 2023-10-06 | Define Backend Architecture
Set Up Database |  |  |  | Not Started | High | 2023-09-25 | 2023-10-06 | Define Backend Architecture
Database Testing |  |  |  | Not Started | High | 2023-09-25 | 2023-10-06 | Create User Model, Create Lesson Model, Set Up Development Enviroment, Set Up Database, Define Backend Architecture
Create User Model |  |  |  | Not Started | Medium | 2023-09-25 | 2023-10-06 | Set Up Database
Sprint Retrospective |  |  | 2023-10-06 | Not Started | Critical ⚠️️
Create Lesson Model |  |  |  | Not Started | Medium | 2023-09-25 | 2023-10-06 | Set Up Database
Client Acceptance |  |  | 2023-10-06 | Not Started | Critical ⚠️️
|  |  | 2023-10-06 |  |  | 2023-09-25 | 2023-10-06
Development Sprint: Lesson
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
Develop Written Content Display |  |  |  | Not Started | Medium | 2023-10-09 | 2023-10-20
Develop Video Player Functionality |  |  |  | Not Started | Medium | 2023-10-09 | 2023-10-20
Develop Responsive Code Practical Lesson |  |  |  | Not Started | Medium | 2023-10-09 | 2023-10-20
Develop Pagination in Lesson |  |  |  | Not Started | Medium | 2023-10-09 | 2023-10-20
Develop Scoring Screen |  |  |  | Not Started | Medium | 2023-10-09 | 2023-10-20 | Final Mockups
Develop Lesson Screen |  |  |  | Not Started | Medium | 2023-10-09 | 2023-10-20 | Final Mockups
User Testing |  |  |  | Not Started
Unit Testing |  |  |  | Not Started | High | 2023-10-09 | 2023-10-20 | Develop Written Content Display, Develop Video Player Functionality, Develop Responsive Code Practical Lesson, Develop Pagination in Lesson, Develop Scoring Screen, Develop Lesson Screen
Functional Testing |  |  |  | Not Started | High | 2023-10-09 | 2023-10-20 | Develop Written Content Display, Develop Video Player Functionality, Develop Pagination in Lesson, Develop Responsive Code Practical Lesson
Sprint Retrospective |  |  | 2023-10-20 | Not Started | Critical ⚠️️ | 2023-10-20 | 2023-10-20
Client Acceptance |  |  | 2023-10-20 | Not Started | Critical ⚠️️ | 2023-10-20 | 2023-10-20
|  |  | 2023-10-20 |  |  | 2023-10-09 | 2023-10-20
Development Sprint: User Profile
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
Develop User Progress Overview |  |  |  | Not Started | Medium | 2023-10-23 | 2023-11-03
Develop User Profile Page View |  |  |  | Not Started | High | 2023-10-23 | 2023-11-03 | Final Mockups
Develop Leave Course Funtionality |  |  |  | Not Started | Medium | 2023-10-23 | 2023-11-03
Develop Add Course Functionality |  |  |  | Not Started | Medium | 2023-10-23 | 2023-11-03
Develop User Progress Badge Display |  |  |  | Not Started | Low | 2023-10-23 | 2023-11-03 | Finalize Images
Develop User Progress Badge Functionality |  |  |  | Not Started | Low | 2023-10-23 | 2023-11-03
Unit Testing |  |  |  | Not Started | High | 2023-10-23 | 2023-11-03 | Develop User Progress Overview, Develop Leave Course Funtionality, Develop User Profile Page View, Develop Add Course Functionality, Develop User Progress Badge Display, Develop User Progress Badge Functionality
Functional Testing |  |  |  | Not Started | High | 2023-10-23 | 2023-11-03 | Develop User Progress Overview, Develop Leave Course Funtionality, Develop User Profile Page View, Develop Add Course Functionality, Develop User Progress Badge Display, Develop User Progress Badge Functionality
Client Acceptance |  |  | 2023-11-03 | Not Started | Critical ⚠️️ | 2023-11-03 | 2023-11-03
Sprint Retrospective |  |  | 2023-11-03 | Not Started | Critical ⚠️️ | 2023-11-03 | 2023-11-03
|  |  | 2023-11-03 |  |  | 2023-10-23 | 2023-11-03
Development Sprint: Landing Page
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
Develop Content Previews |  |  |  | Not Started | Medium | 2023-11-06 | 2023-11-17 | Final Mockups
Develop Push Notifications |  |  |  | Not Started | Medium | 2023-11-06 | 2023-11-17
Develop Content Cards |  |  |  | Not Started | Medium | 2023-11-06 | 2023-11-17 | Final Mockups
Develop Landing Page Screen |  |  |  | Not Started | Medium | 2023-11-06 | 2023-11-17 | Final Mockups
Unit Testing |  |  |  | Not Started | High | 2023-11-06 | 2023-11-17
Functional Testing |  |  |  | Not Started | High | 2023-11-06 | 2023-11-17
Sprint Retrospective |  |  | 2023-11-17 | Not Started | Critical ⚠️️ | 2023-11-17 | 2023-11-17
Client Acceptance |  |  | 2023-11-17 | Not Started | Critical ⚠️️ | 2023-11-17 | 2023-11-17
|  |  | 2023-11-17 |  |  | 2023-11-06 | 2023-11-17
Development Sprint: Navigation
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
Develop Navigation/ Menu Bar |  |  |  | Not Started | Medium | 2023-11-20 | 2023-12-01 | Final Mockups
Develop Bottom Navigation /Footer |  |  |  | Not Started | Low | 2023-11-20 | 2023-12-01 | Final Mockups
Develop Navigation Functionality |  |  |  | Not Started | High | 2023-11-20 | 2023-12-01 | Final Mockups
Unit Testing |  |  |  | Not Started | High | 2023-11-20 | 2023-12-01
Functional Testing |  |  |  | Not Started | High | 2023-11-20 | 2023-12-01
Integration Testing |  |  |  | Not Started | High | 2023-11-20 | 2023-12-01
Sprint Retrospective |  |  | 2023-12-01 | Not Started | Critical ⚠️️ | 2023-12-01 | 2023-12-01
Client Acceptance |  |  | 2023-12-01 | Not Started | Critical ⚠️️ | 2023-12-01 | 2023-12-01
|  |  | 2023-12-01 |  |  | 2023-11-20 | 2023-12-01
Development Sprint: Login/ Sign Up
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
Develop Sign in/ Log in Functionality |  |  |  | Not Started | High | 2023-12-04 | 2023-12-15
Develop Sign In Page |  |  |  | Not Started | Medium | 2023-12-04 | 2023-12-15 | Final Mockups
Develop Log In Form |  |  |  | Not Started | High | 2023-12-04 | 2023-12-15
Develop Log In Page |  |  |  | Not Started | Medium | 2023-12-04 | 2023-12-15 | Final Mockups
Develop Sign In Form |  |  |  | Not Started | High | 2023-12-04 | 2023-12-15
Unit Testing |  |  |  | Not Started | Medium | 2023-12-04 | 2023-12-15
Integration Testing |  |  |  | Not Started | High | 2023-12-04 | 2023-12-15
Functional Testing |  |  |  | Not Started | High | 2023-12-04 | 2023-12-15
Sprint Retrospective |  |  | 2023-12-15 | Not Started | Critical ⚠️️ | 2023-12-15 | 2023-12-15
Client Acceptance |  |  | 2023-12-15 | Not Started | Critical ⚠️️ | 2023-12-15 | 2023-12-15
|  |  | 2023-12-15 |  |  | 2023-12-04 | 2023-12-15
Development Sprint: Backend User Overview
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
Develop Screen User View |  |  |  | Not Started | Medium | 2023-12-18 | 2024-01-05
Develop Screen All Users |  |  |  | Not Started | Medium | 2023-12-18 | 2024-01-05
Develop User Queries |  |  |  | Not Started | Medium | 2023-12-18 | 2024-01-05
Unit Testing |  |  |  | Not Started | Medium | 2023-12-18 | 2024-01-05
Functional Testing |  |  |  | Not Started | Medium | 2023-12-18 | 2024-01-05
Integration Testing |  |  |  | Not Started | Medium | 2023-12-18 | 2024-01-05
Sprint Retrospective |  |  | 2024-01-05 | Not Started | Critical ⚠️️ | 2024-01-05 | 2024-01-05
Client Acceptance |  |  | 2024-01-05 | Not Started | Critical ⚠️️ | 2024-01-05 | 2024-01-05
|  |  | 2024-01-05 |  |  | 2023-12-18 | 2024-01-05
Development Sprint: Backend Mailing List
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
Develop Mailing List Form |  |  |  | Not Started | High | 2024-01-08 | 2024-01-19
Develop Mailing List Send Mass Email Function |  |  |  | Not Started | High | 2024-01-08 | 2024-01-19
Develop Mailing List Sort/ Select Users |  |  |  | Not Started | Medium | 2024-01-08 | 2024-01-19
Develop Screen Mailing List - Write Email |  |  |  | Not Started | Medium | 2024-01-08 | 2024-01-19
Develop Screen - Sort/ Search Users |  |  |  | Not Started | Medium | 2024-01-08 | 2024-01-19
Unit Testing |  |  |  | Not Started | High | 2024-01-08 | 2024-01-19
Function Testing |  |  |  | Not Started | High | 2024-01-08 | 2024-01-19
Integration Testing |  |  |  | Not Started | High | 2024-01-08 | 2024-01-19
Sprint Retrospective |  |  | 2024-01-19 | Not Started | Critical ⚠️️ | 2024-01-19 | 2024-01-19
Client Acceptance |  |  | 2024-01-19 | Not Started | Critical ⚠️️ | 2024-01-19 | 2024-01-19
|  |  | 2024-01-19 |  |  | 2024-01-08 | 2024-01-19
Development Sprint: Backend Content Overview
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
Develop Edit Content Functionality |  |  |  | Not Started | High | 2024-01-22 | 2024-02-02
Develop Edit Content Screen |  |  |  | Not Started | Medium | 2024-01-22 | 2024-02-02
Function Testing |  |  |  | Not Started | High | 2024-01-22 | 2024-02-02
Integration Testing |  |  |  | Not Started | High | 2024-01-22 | 2024-02-02
Unit Testing |  |  |  | Not Started | High | 2024-01-22 | 2024-02-02
Sprint Retrospective |  |  | 2024-02-02 | Not Started | Critical ⚠️️ | 2024-02-02 | 2024-02-02
Client Acceptance |  |  | 2024-02-02 | Not Started | Critical ⚠️️ | 2024-02-02 | 2024-02-02
|  |  | 2024-02-02 |  |  | 2024-01-22 | 2024-02-02
Testing Whole Application
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
Integration Testing |  |  |  | Not Started | High | 2024-02-05 | 2024-02-16 | Upload Content as Lessons to Database
System Testing |  |  |  | Not Started | High | 2024-02-05 | 2024-02-16 | Upload Content as Lessons to Database
Acceptance Testing |  |  |  | Not Started | High | 2024-02-05 | 2024-02-16 | Upload Content as Lessons to Database
Performance Testing |  |  |  | Not Started | High | 2024-02-05 | 2024-02-16 | Upload Content as Lessons to Database
User Testing |  |  |  | Not Started | High | 2024-02-05 | 2024-02-16 | Upload Content as Lessons to Database
Sprint Retrospective |  |  | 2024-02-16 | Not Started | Critical ⚠️️ | 2024-02-16 | 2024-02-16
Client Acceptance |  |  | 2024-02-16 | Not Started | Critical ⚠️️ | 2024-02-16 | 2024-02-16
|  |  | 2024-02-16 |  |  | 2024-02-05 | 2024-02-16
Content Creation Sprint: Requirements
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
Elicit Content Requirements |  |  | 2023-09-05 | Not Started | Medium | 2023-09-04 | 2023-09-08
Draft Overview of Content |  |  | 2023-09-08 | Not Started | High | 2023-09-04 | 2023-09-08 | Elicit Content Requirements
Sprint Retrospective |  |  | 2023-09-08 | Not Started |  | 2023-09-08 | 2023-09-08
Client Acceptance |  |  | 2023-09-08 | Not Started | Critical ⚠️️ | 2023-09-08 | 2023-09-08
|  |  | 2023-09-05 to 2023-09-08 |  |  | 2023-09-04 | 2023-09-08
Content Creation Sprint: Initial Draft
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
Draft Video Content |  |  |  | Not Started | High | 2023-09-11 | 2023-09-22 | Draft Overview of Content
Draft Video Scripts |  |  |  | Not Started | High | 2023-09-11 | 2023-09-22 | Draft Overview of Content
Draft Written Content |  |  |  | Not Started | Medium | 2023-09-11 | 2023-09-22 | Draft Overview of Content
Draft Interactive Exercises |  |  |  | Not Started | Medium | 2023-09-11 | 2023-09-22 | Draft Overview of Content
Sprint Retrospective |  |  | 2023-09-22 | Not Started |  | 2023-09-22 | 2023-09-22
Client Acceptance |  |  | 2023-09-22 | Not Started | Critical ⚠️️ | 2023-09-22 | 2023-09-22
|  |  | 2023-09-22 |  |  | 2023-09-11 | 2023-09-22
Content Creation Sprint: Version One
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
First Version Written Content |  |  |  | Not Started |  | 2023-09-25 | 2023-09-29 | Draft Written Content
First Version Interactive Exercises |  |  |  | Not Started |  | 2023-09-25 | 2023-09-29 | Draft Interactive Exercises
First Version Video Scripts |  |  |  | Not Started |  | 2023-09-25 | 2023-09-29 | Draft Video Scripts
Sprint Retrospective |  |  | 2023-09-29 | Not Started |  | 2023-09-29 | 2023-09-29
Client Acceptance |  |  | 2023-09-29 | Not Started | Critical ⚠️️ | 2023-09-29 | 2023-09-29
|  |  | 2023-09-29 |  |  | 2023-09-25 | 2023-09-29
Content Creation Sprint: Version Two
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
Second Version Written Content |  |  |  | Not Started |  | 2023-10-02 | 2023-10-06 | First Version Written Content
Final Version Video Scripts |  |  |  | Not Started |  | 2023-10-02 | 2023-10-06 | First Version Video Scripts
Second Version Interactive Content |  |  |  | Not Started |  | 2023-10-02 | 2023-10-06 | First Version Interactive Exercises
Sprint Retrospective |  |  | 2023-10-06 | Not Started |  | 2023-10-06 | 2023-10-06
Client Acceptance |  |  | 2023-10-06 | Not Started | Critical ⚠️️ | 2023-10-06 | 2023-10-06
|  |  | 2023-10-06 |  |  | 2023-10-02 | 2023-10-06
Content Creation Sprint: Version 3
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
Film Video Content |  |  |  | Not Started | High | 2023-10-09 | 2023-10-20 | Final Version Video Scripts
Final Written Content |  |  |  | Not Started | Medium | 2023-10-09 | 2023-10-20
Final Interactive Content |  |  |  | Not Started | Medium | 2023-10-09 | 2023-10-20 | Second Version Interactive Content
Sprint Retrospective |  |  | 2023-10-20 | Not Started |  | 2023-10-20 | 2023-10-20
Client Acceptance |  |  | 2023-10-20 | Not Started |  | 2023-10-20 | 2023-10-20
|  |  | 2023-10-20 |  |  | 2023-10-09 | 2023-10-20
Content Creation Sprint: Version 4
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
Edit Video Content |  |  |  | Not Started |  | 2023-10-23 | 2023-11-03
Sprint Retrospective |  |  |  | Not Started |  | 2023-11-03 | 2023-11-03
Client Acceptance |  |  |  | Not Started |  | 2023-11-03 | 2023-11-03
[6 empty] | 2023-10-23 | 2023-11-03
Content Creation Sprint: Version 5
Name | Subtasks | Owner | Due Date | Status | Priority | Timeline - Start | Timeline - End | Dependency
Upload Content as Lessons to Database |  |  |  | Not Started | Medium | 2023-11-06 | 2023-11-17 | Set Up Database, Create Lesson Model
Client Acceptance |  |  | 2023-11-17 | Not Started | Critical ⚠️️ | 2023-11-17 | 2023-11-17
Sprint Retrospective |  |  | 2023-11-17 | Not Started | Critical ⚠️️ | 2023-11-17 | 2023-11-17
|  |  | 2023-11-17 |  |  | 2023-11-06 | 2023-11-17