## v1 (2)
Category | Description | Estimated Cost (NZD) | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
Development
- Android App Development | cost of development of back end software ,plugin, database etc | 18600 | 3100 | 3100 | 3100 | 3100 | 3100 | 3100
Design
- UI/UX Design | cost of development of front end design of software | 7500 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250
- Graphic Design | cost of creating assists like logo, theme, icon etc | 1800 | 600 | 600 | 600 | 0 | 0 | 0
Content Creation
- Text, Audio, Video Content | cost of creating content for tutorial | 5400 | 900 | 900 | 900 | 900 | 900 | 900
Hosting and Infrastructure
- Cloud Hosting | cost of setting up web hosting and server setup | 2000 | 0 | 0 | 500 | 500 | 500 | 500
Quality Assurance and Testing
- Testing and QA | cost for testing software sprint | 1500 | 0 | 300 | 300 | 300 | 300 | 300
Miscellaneous
- Legal and Compliance | cost for consulting legal compliances regarding the educational web content in new Zealand bylaws | 1000 | 500 | 0 | 0 | 0 | 500 | 0
- Contingency (10% of total budget) |  | 3000 | 500 | 500 | 500 | 500 | 500 | 500
Office Infrastructure Costs
- Office Rent | $200 per seat for 3 full time staff | 3600 | 600 | 600 | 600 | 600 | 600 | 600
- Travel Expenses |  | 3600 | 0 | 1200 | 0 | 1200 | 0 | 1200
- Office Amenities (Tea, Coffee, etc.) |  | 3000 | 500 | 500 | 500 | 500 | 500 | 500
Total Budget |  | 51000 | 7950 | 8950 | 8250 | 8850 | 8150 | 8850
0
|  |  | Month 1: Hours | Cost
| List Of employees/Freelancer | Tota No of Hours required | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Per Hour Rate | Total Cost | List Of employees/Freelancer | Tota No of Hours required | Per Hour Rate | Total Cost | Per Hour Rate | Total Cost
Development
- Android App Development |  | 390 | 65 | 65 | 65 | 65 | 65 | 65 | 3100 | 3100 | 3100 | 3100 | 3100 | 3100
| Senior developer | 150 | 25 | 25 | 25 | 25 | 25 | 25 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 60 | 9000 | Senior developer | 150 | 60 | 9000 | 100 | 15000
| Junior developer | 240 | 40 | 40 | 40 | 40 | 40 | 40 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 40 | 9600 | Junior developer | 240 | 40 | 9600 | 70 | 16800
Design |  | 150 | 25 | 25 | 25 | 25 | 25 | 25 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250
- UI/UX Design
| Senior desginer | 150 | 25 | 25 | 25 | 25 | 25 | 25 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 50 | 7500 | Senior desginer | 150 | 50 | 7500 | 80 | 12000
- Graphic Design |  | 60 | 20 | 20 | 20 | 0 | 0 | 0 | 600 | 600 | 600 | 0 | 0 | 0
| Freelancer | 60 | 20 | 20 | 20 | 0 | 0 | 0 | 600 | 600 | 600 | 0 | 0 | 0 | 30 | 1800 | Freelancer | 60 | 30 | 1800 | 50 | 3000
Content Creation |  | 180 | 30 | 30 | 30 | 30 | 30 | 30 | 900 | 900 | 900 | 900 | 900 | 900
- Text, Audio, Video Content
| Freelancer- Text Content | 60 | 10 | 10 | 10 | 10 | 10 | 10 | 300 | 300 | 300 | 300 | 300 | 300 | 30 | 1800 | Freelancer- Text Content | 60 | 30 | 1800 | 50 | 3000
| Freelancer-Audio Content | 60 | 10 | 10 | 10 | 10 | 10 | 10 | 300 | 300 | 300 | 300 | 300 | 300 | 30 | 1800 | Freelancer-Audio Content | 60 | 30 | 1800 | 50 | 3000
| Freelancer-Video Content | 60 | 10 | 10 | 10 | 10 | 10 | 10 | 300 | 300 | 300 | 300 | 300 | 300 | 30 | 1800 | Freelancer-Video Content | 60 | 30 | 1800 | 50 | 3000
[17 empty] | cost of develoment |  |  | 33300 |  | 55800
[17 empty] | office administrative and setup cost |  |  | 17700 |  | 17700
[17 empty] | Total Cost |  |  | 51000 |  | 73500

## v1
Category | Description | Estimated Cost (NZD) | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
Development
- Android App Development | cost of development of back end software ,plugin, database etc | 31800 | 5300 | 5300 | 5300 | 5300 | 5300 | 5300
Design
- UI/UX Design | cost of development of front end design of software | 12000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
- Graphic Design | cost of creating assists like logo, theme, icon etc | 3000 | 1000 | 1000 | 1000 | 0 | 0 | 0
Content Creation
- Text, Audio, Video Content | cost of creating content for tutorial | 9000 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
Hosting and Infrastructure
- Cloud Hosting | cost of setting up web hosting and server setup | 2000 | 0 | 0 | 500 | 500 | 500 | 500
Quality Assurance and Testing
- Testing and QA | cost for testing software sprint | 1500 | 0 | 300 | 300 | 300 | 300 | 300
Miscellaneous
- Legal and Compliance | cost for consulting legal compliances regarding the educational web content in new Zealand bylaws | 1000 | 500 | 0 | 0 | 0 | 500 | 0
- Contingency (10% of total budget) |  | 3000 | 500 | 500 | 500 | 500 | 500 | 500
Office Infrastructure Costs
- Office Rent | $200 per seat for 3 full time staff | 3600 | 600 | 600 | 600 | 600 | 600 | 600
- Travel Expenses |  | 3600 | 0 | 1200 | 0 | 1200 | 0 | 1200
- Office Amenities (Tea, Coffee, etc.) |  | 3000 | 500 | 500 | 500 | 500 | 500 | 500
Total Budget |  | 73500 | 11900 | 12900 | 12200 | 12400 | 11700 | 12400
0
|  |  | Month 1: Hours | Cost
| List Of employees/Freelancer | Tota No of Hours required | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Per Hour Rate | Total Cost
Development
- Android App Development |  | 390 | 65 | 65 | 65 | 65 | 65 | 65 | 5300 | 5300 | 5300 | 5300 | 5300 | 5300
| Senior developer | 150 | 25 | 25 | 25 | 25 | 25 | 25 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 100 | 15000
| Junior developer | 240 | 40 | 40 | 40 | 40 | 40 | 40 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 70 | 16800
Design |  | 150 | 25 | 25 | 25 | 25 | 25 | 25 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
- UI/UX Design
| Senior desginer | 150 | 25 | 25 | 25 | 25 | 25 | 25 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 80 | 12000
- Graphic Design |  | 60 | 20 | 20 | 20 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 0 | 0 | 0
| Freelancer | 60 | 20 | 20 | 20 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 50 | 3000
Content Creation |  | 180 | 30 | 30 | 30 | 30 | 30 | 30 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
- Text, Audio, Video Content
| Freelancer- Text Content | 60 | 10 | 10 | 10 | 10 | 10 | 10 | 500 | 500 | 500 | 500 | 500 | 500 | 50 | 3000
| Freelancer-Audio Content | 60 | 10 | 10 | 10 | 10 | 10 | 10 | 500 | 500 | 500 | 500 | 500 | 500 | 50 | 3000
| Freelancer-Video Content | 60 | 10 | 10 | 10 | 10 | 10 | 10 | 500 | 500 | 500 | 500 | 500 | 500 | 50 | 3000